## Story
Name | Status | Description
V2 REST pt 1 | IN PRG | The purpose of this is to allow images to be selected from a directory in the images folder rather than only at the top level.
V2 REST pt 2 | READY | The purpose of this is to allow playlists to be stored and selected from a directory rather than just in a flat structure.
Playlist Settings | NO READY | There might be playlist specific settings that are not General Settings
General Settings | READY | There will be general settings such as the number of LEDs on the device
Tidy UI
Tidy Server

## Issues
# | Seq | Priority | Status | Status Date | Type | Title | Requires | Story | Description
1 |  | 2 | DONE |  |  | Track Disable Client |  |  | Want to be able to have a temporary omit on a track that stops it from playing. This would mean that I would not have to delete if from the track and re-add (from a nested directory) it to turn it off and on.
2 |  | 1 | DONE |  |  | Speed | 35 | General Settings | Need to have a play speed on the playlist so that I can vary the movement rate. Hamburger Menu
3 |  | 1 | DONE |  |  | Brightness | 35 | General Settings | Would be good to have an overall brightness Hamburger Menu
4 |  |  | DONE |  | UI |  |  | Tidy UI | Image directory Browser should display the name of the current directory
5 |  |  | DONE |  | Arch | Remove REST v1/images |  |  | Remove REST v1/images
6 |  |  | DONE |  | UI | Tidy image browser buttons |  | Tidy UI | Make buttons on image browser not full width … like the ones on the home page
7 |  |  | DONE |  | UI | Make browse playlist mode visible |  | Tidy UI
8 |  |  | DONE |  | UI | Add playlist |  | Tidy UI | make heading h4 and buttons same as on home
9 |  |  | DONE |  | BUG |  |  |  | Cant save newly created playlist
10 |  |  | DONE |  | UI | Play Playlist tidy |  | Tidy UI | H4 and button layout on play playlist screen
11 |  |  | DONE |  | Server | Exception on directory images |  |  | Exception on playing images in directories
12 |  |  | DONE |  | UI | Better navigation from edit to play |  |  | Better navigation from edit to play
13 |  | 2 | DONE |  |  |  | 24 |  | Better Top Navigation … title and hamburger. No code change … fixed as consequnce of other changes
44 |  | 1 | DONE |  |  | Server side handling for config |  | General Settings | Server side handling for config. Split into 53 and 56
15 |  |  | DONE |  | tech | remove dirname from path |  |  | Remove dirname from browse images path in app.module.ts
16 |  | 2 | DONE |  |  | diasble tracks in play mode |  |  | In play mode want to be able to disable tracks Duplicate of 1
17 |  | 1 | DONE |  |  | add return option to nav | 18
18 |  |  | DONE |  |  | need header component |  |  | Break header into own component so can drive behaviour
19 |  | 1 | DONE |  |  | select/unselect all in directory bar |  |  | on browse for images need to put the select all and un select all as buttons on the directory bar to save two buttons on the list at the bottom.
20 |  | 1 | DONE |  |  | images to playlist return nav |  |  | add return from images to playlist on navbar
21 |  | 1 | DONE |  | BUG | don’t add directory to playlist |  |  | When adding all images it also adds the directory
22 |  | 1 | DONE |  | BUG |  |  |  | Playlist save not working. This was caused by Bitdefender Safe Files
24 |  | 1 | DONE |  | UI | Hamburger Menu |  |  | Add Hamburger menu to top
67 |  | 1 | DONE |  |  | server implementaiton of debounce config from client
70 |  | 1 | PENDING |  |  | UI |  |  | add image should only show one select all remove all button at a time
27 |  | 1 | CLOSED |  |  | Hearbeat | 35 |  | Settings option to allow for connectivity to REST server to be established - non needed as there is now the poll for change
28 |  | 2 | DONE |  |  | icons same size |  |  | Should make the tick/cross icons the same size so they do not move the screen when they are changeg
29 |  | 2 | DONE |  |  | Should add return from browse playlist to main menu
30 |  | 2 | DONE |  |  | Should have an return nav bar on add playlist
31 |  | 1 | DONE |  | arch | Repackage pages and pageComponents should be separate
32 |  | 3 | CLOSED |  |  | message/alert component |  |  | based on timed messages and success/failure this has been done
39 |  | 3 | CLOSED |  |  | need a way to kill and restart server from browser |  |  | need a way to kill and restart server from browser . this is covered by the move to the new model
33 |  | 2 | DONE |  |  | icon config |  |  | move the config styles for icons into config and icon width
35 |  | 1 | DONE |  |  | Blank settings page |  |  | Settings page placehold for other stuff
36 |  | 1 | DONE |  |  | REST server check |  |  | Check connectivity to Server on settings page
37 |  | 1 | DONE |  |  | REST ping service | 37 |  | Add a rest ping service
38 |  | 1 | DONE |  | Bug | plus on add image is cross
43 |  | 2 | CLOSED |  |  | Prevent playing unsaved data |  |  | encapsulate playlist into a model and protect the data
72 |  | 1 | CLOSED |  |  | Edit playlist starts dirty |  |  | This is not the case
41 |  | 2 | DONE |  |  | Add track disable to server
42 |  | 1 | DONE |  |  | upgrade Playlist to use Message Component |  |  | Make the playlist save and play errors use the Message component
74 |  | 1 | PENDING |  |  | Should not be able to navigate from Edit Playlist and have Playlist dirty |  |  | The browse list makes it clear that it is not saved
90 |  | 1 | DONE |  |  | visual acknowledgement of startup
45 |  | 1 | DONE |  | issue | need to debounce button
46 |  | 1 | DONE |  | arch | move /app to /
58 |  | 2 | DONE |  | arch | uniform message handling |  |  | add playlist page should use message page component
48 |  | 1 | DONE |  | bug | ng bulid failure
91 |  | 1 | DONE |  |  | auto startup
47 |  | 1 | DONE |  | arch | handle 404 |  |  | see https://expressjs.com/en/starter/faq.html on 404 and under static and fallthrough and https://stackoverflow.com/questions/9321027/how-to-send-files-with-node-js for sending file
51 | 2 | 3 | DONE |  |  | Need to be able to config debounce timeout |  | General Settings
52 |  | 2 | DONE |  | arch | REST service for get config |  | General Settings
53 |  | 2 | DONE |  | arch | REST service for set config |  | General Settings
54 | 1 | 2 | DONE |  | arch | repository service for get config |  | General Settings
55 |  | 2 | DONE |  | arch | repository service for set config |  | General Settings
56 |  | 2 | DONE |  | arch | update internals based on post config
57 |  |  | DONE |  | UI | modal library inclusion
92 |  | 1 | DONE |  |  | Test button in setting text too long
59 |  |  | CLOSED |  |  | should add message when navigating away from playlist and playlist needs saving |  |  | covered by playlist model
60 |  | 5 | CLOSED |  | arch | of |  |  | import { Observable } from 'rxjs/Observable'; import 'rxjs/add/observable/of'; Couldn’t get this to work easily … closing it to cut down noise
49 |  | 3 | DONE |  | UI | piW fav icon
62 |  |  | DONE |  | arch | playlist model
63 |  | 1 | DONE |  | arch | emulator to share same server as main |  |  | means that there are not two ports
50 |  | 3 | DONE |  | arch | run on port 80
65 |  |  | DONE |  |  | version numbers on saved playlist
66 |  |  | DONE |  |  | handle error in Repository services
64 |  | 3 | CLOSED |  |  | angular logging |  |  | Duplicate of 80
68 |  |  | DONE |  |  | when updating config need to reload playlist
93 |  | 1 | DONE |  |  | Nav bar not displaying proplerly on Samsung S7 edge
77 |  | 1 | DONE |  | feature | duplicate track from edit playlist screen | see 83
71 |  | 1 | DONE |  |  | use new model |  |  | moveup and move down of tracks should take advantage of the new model
69 |  | 1 | DONE |  |  | speed/brightness per image | see 101 | V2 REST pt 2 | client side
80 |  | 3 | DONE |  | arc | client side logging | 26 |  | use node debug
81 |  | 3 | DONE |  | arc | server side logging |  |  | use node debug
61 |  |  | CLOSED |  |  | remove checks for null playlists |  |  | not erally sure what this refers to anymore
76 |  | 1 | DONE |  | BUT | Add selected tracks does not mark playlist as dirty
125 |  | 1 | DONE | 2018-04-26 |  | Extract Player from Playlist
78 |  | 1 | DONE |  |  | Config issues stopping ng build
79 |  |  | DONE |  |  | display name should have * from model
113 |  | 1 | DONE | 2018-04-24 |  | Horizontal flip/Vertical flip image |  |  | fas fa-arrows-alt-v, fas fa-arrows-alt-h from fontawesome https://www.w3schools.com/howto/howto_css_flip_image.asp JIMP image.flip( horz, vert ); // flip the image horizontally or vertically
123 |  | 1 | DONE | 2018-04-29 |  | scale images |  |  | and rotate from 101
131 |  | 1 | DONE | 2018-05-11 |  | Build release using typescript
83 |  |  | DONE |  |  | fortawesome |  |  | upgrade font awesome to v5
84 |  | 1 | DONE |  |  | remove model demo from front screen
85 |  | 1 | DONE |  |  | reload path does not work |  |  | it loads an empty playlist
86 |  | 1 | DONE |  |  | resolve cricular build dependency
87 |  | 1 | DONE |  | bug | TypeError: Converting circular structure to JSON
88 |  | 1 | DONE |  | bug | demo page not working in server emulator
126 |  | 1 | DONE | 2018-04-29 |  | Should have a PlaylistDTOToPlaylist mapper that takes NUMLEDS and brigtness |  |  | This will remove a lot of stuff in the final Playlist that does not need to be there (config, newPlaylist) this version uses config see 129 also
122 |  | 1.1 | DONE | 2018-04-25 |  | Extract Playlist class
119 |  | 1.2 | DONE | 2018-04-25 |  | Use typescript on server | do after 122 |  | For ServerCommon
82 |  | 5 | CLOSED |  |  | angualize |  |  | make models and mappers angular services (DTOs should be fine) if that makes sense
89 |  | 5 | PENDING |  |  | use material design
94 |  | 1 | DONE |  |  | track icons squashed on small screen
95 |  | 2 | DONE |  |  | autostartup in rc.local
103 |  | 2 | DONE |  |  | range sliders for config |  |  | https://www.w3schools.com/howto/howto_js_rangeslider.asp
120 |  | 1.3 | CLOSED | 2018-04-29 |  | Share DTOs between client and server | do after 119 |  | this is done on a copy and paste basis
112 |  | 2 | CLOSED | 2018-04-24 |  | Missing lines effect |  |  | Would do this pre prod in PhotoShop
101 |  | 2 | CLOSED | 2018-04-27 |  | rotate images | see 25 |  | On UI just have a one of 4 arrows showing, absorbed into 123
100 |  | 1 | DONE |  |  | On play playlist screen should only show the elements that are enabled
137 |  | 1 | DONE |  |  | Alignment option on detail edit of image missing from pi version |  |  | This was fixed with the iconmoon changes
138 |  | 1 | DONE | 2018-05-16 |  | What to do with serverEmulator … delete it or reinstate it |  |  | Delete it
124 |  | 2 |  |  |  | Use pure virtual functions
130 |  | 2 |  |  |  | Ability to sheer picture
115 |  | 2 |  |  |  | Groups in playlist |  |  | Where you can resize, reverse, flipY the group as a whole
109 |  | 2 | DONE | 2018-05-09 |  | Slider pipe for values |  |  | Have gone some way to this with the round … probably just need to add parameters to this … number.toFixed(2) looks promising. NOTE this will not be done using a pipe
73 |  | 2 |  |  |  | Playlist names should not have .json |  | V2 REST pt 2
108 |  | 1 | DONE |  |  | Advanced config space on edit page
75 |  | 2 |  |  |  | Refetch playlist from server
110 |  | 1 | DONE |  |  | Speed/brightness per image | see 101, 69 | V2 REST pt 2 | server side
111 |  | 1 | DONE |  |  | hr issue on advanced track detasil |  |  | might need to move the advanced tab from track to playlist so that it is outside the ul
134 |  | 2 |  |  |  | Rejig config service to be better | 132 |  | currently it is not really a service … should be a singleton. probably want to have clientConfig, commonConfig and other config (from Emulator or Rpi) passed in as parameters
14 |  | 3 |  |  |  | Playlist Folders |  | V2 REST pt 2 | Enable playlist folders
31 |  | 3 |  |  | arch | styles to css
26 |  | 3 |  |  | arch | REST error handling |  | Error Handling | Better error handling when REST server not availableThere is a better approach but this is not done everyhwere yet. This still needs to be done for the repo fetches of data It is kind of obvious as there is no data … and there is the settings option to test connectivity Makes sens to add this when going over the code putting in logging
116 |  | 1 | DONE | 2018-04-24 |  | Use typescript on server |  |  | For ServerEmulator
117 |  | 1 | DONE | 2018-04-24 |  | remove unneeded calls in Track.component.ts and have better naming
118 |  | 1 | DONE | 2018-04-24 |  | Play/save/add track button visible when showing details of track
121 |  | 3 | DONE | 2018-05-09 |  | tslint |  |  | Initial implementation and pass through of code
96 |  | 3 |  |  |  | get Release text into client |  |  | Poss look at using git log being called from a rest service
104 |  | 3 |  |  |  | remove repository.service.ts |  |  | refactor into another component
105 |  | 3 |  |  |  | use single quote style in html
40 |  | 4 |  |  | bug | hamburger feature |  |  | pressing hambuger on settings takes you to main
25 |  | 4 |  |  | UI | slide transistion |  |  | Add slide transitions
102 |  | 4 |  |  |  | touch drag and drop |  |  | https://stackoverflow.com/questions/5186441/javascript-drag-and-drop-for-touch-devices https://medium.com/@asm/animated-slide-panel-with-angular-e985ad646f9
97 |  | 5 |  |  |  | Better place for IssuesLog
127 |  | 5 | DONE | 2018-04-26 | arch | node debugger
98 |  | 5 |  |  |  | don’t have std in in daemon |  |  | https://stackoverflow.com/questions/7783341/run-script-with-rc-local-script-works-but-not-at-boot
99 |  | 5 | DONE |  |  | faster boot time for r PI |  |  | With the change to the compiled ts the boot time is down to 30s which is sufficient at the moment.
106 |  | 5 |  |  |  | Testing
129 |  | 5 | DONE | 2018-05-09 |  | Should have a PlaylistDTOToPlaylist mapper that takes NUMLEDS and brigtness | see 124, and 128
132 |  | 1 | QUESTIONABLE |  |  | Should merge serverEmulator into serverCommon to make the build/dev cycle easier | revist after 134 |  | don’t forget to update the README.md file with the build instructions when you do I don’t really want the emulator code in the real version I do want the emulator code to call the server in the same way that Rpi will
133 |  | 2 | DONE | 2018-05-01 |  | be consistent with the import/export of modules |  |  | use export class …
107 |  | 5 |  |  |  | Config Service should return min, max, value for items
114 |  | 5 |  |  |  | Fix header at top
128 |  | 5 |  |  |  | default {} parameters | see 124, and 128
135 |  | 5 | DONE |  |  | Have better alternative for font awesome |  |  | using https://stackoverflow.com/questions/19401633/how-to-fire-an-event-on-class-change-using-jquery see notes on 5/5/2018 This was done when the iconmoon change went in
136 |  | 5 |  |  |  | remove imports
139 |  | 1 | DONE | 2018-05-11 |  | copy index.html to correct place during build
140 |  | 1 | DONE | 2018-05-12 |  | proper fix for alingnment icon
141 |  | 1 | DONE | 2018-05-14 |  | Add right pad to image so that can then have repeat with pause. |  |  | Note this is a server and client change
142 |  | 2 | DONE | 2018-05-16 |  | TrackDTO and PlaylistDTO have different names on the server and the client app
143 |  | 1 | DONE | 2018-05-16 |  | ServerInfo server side
144 |  | 1 | DONE | 2018-05-18 |  | ServerInfo client side
145 |  | 1 | DONE | 2018-05-23 |  | ServerInfo Rpi
146 |  | 2 | DONE | 2018-05-18 |  | in editor wrapGet should be moved to the utilities package
147 |  | 2 |  |  |  | Config in serverCommon should be moved to its own package
148 |  | 2 |  |  |  | serverInfoDTO in editor should be reused in server
149 |  | 1 | DONE | 2018-05-18 |  | move wrap post to utilities
150 |  | 1 |  |  |  | Playlistrepo should use get Wrapped methods in utility
151 |  | 1 | DONE | 2018-05-21 |  | Better image handling on client using JIMP
152 |  | 1 | DONE | 2018-05-22 |  | Client side recolor and stripes
153 |  | 1 |  |  |  | Server side recolor and stripes
154 |  | 1 | DONE | 2018-05-23 |  | Angular app build error |  |  | srcOut needed to be public