## Story
Name | Status | Description
V2 REST pt 1 | IN PRG | The purpose of this is to allow images to be selected from a directory in the images folder rather than only at the top level.
V2 REST pt 2 | READY | The purpose of this is to allow playlists to be stored and selected from a directory rather than just in a flat structure.
Playlist Settings | NO READY | There might be playlist specific settings that are not General Settings
General Settings | READY | There will be general settings such as the number of LEDs on the device
Tidy UI
Tidy Server

## Issues
# | Priority | Status | Type | Name | Requires | Story | Description
1 | 2 |  |  | Track Disable |  |  | Want to be able to have a temporary omit on a track that stops it from playing. This would mean that I would not have to delete if from the track and re-add (from a nested directory) it to turn it off and on.
2 | 2 |  |  | Speed | 24 | General Settings | Need to have a play speed on the playlist so that I can vary the movement rate. Hamburger Menu
3 | 2 |  |  | Brightness |  | General Settings | Would be good to have an overall brightness Hamburger Menu
4 |  | DONE | UI |  |  | Tidy UI | Image directory Browser should display the name of the current directory
5 |  | DONE | Arch | Remove REST v1/images |  |  | Remove REST v1/images
6 |  | DONE | UI | Tidy image browser buttons |  | Tidy UI | Make buttons on image browser not full width … like the ones on the home page
7 |  | DONE | UI | Make browse playlist mode visible |  | Tidy UI
8 |  | DONE | UI | Add playlist |  | Tidy UI | make heading h4 and buttons same as on home
9 |  | DONE | BUG |  |  |  | Cant save newly created playlist
10 |  | DONE | UI | Play Playlist tidy |  | Tidy UI | H4 and button layout on play playlist screen
11 |  | DONE | Server | Exception on directory images |  |  | Exception on playing images in directories
12 |  | DONE | UI | Better navigation from edit to play |  |  | Better navigation from edit to play
13 | 2 |  |  |  | 24 |  | Better Top Navigation … title and hamburger
14 | 3 |  |  |  |  | V2 REST pt 2 | Enabple playlist folders
15 |  | DONE | tech | remove dirname from path |  |  | Remove dirname from browse images path in app.module.ts
16 | 2 | DONE |  | diasble tracks in play mode |  |  | In play mode want to be able to disable tracks Duplicate of 1
17 | 1 | DONE |  | add return option to nav | 18
18 |  | DONE |  | need header component |  |  | Break header into own component so can drive behaviour
19 | 1 | DONE |  | select/unselect all in directory bar |  |  | on browse for images need to put the select all and un select all as buttons on the directory bar to save two buttons on the list at the bottom.
20 | 1 | DONE |  | images to playlist return nav |  |  | add return from images to playlist on navbar
21 | 1 | DONE | BUG | don’t add directory to playlist |  |  | When adding all images it also adds the directory
22 | 1 | DONE | BUG |  |  |  | Playlist save not working. This was caused by Bitdefender Safe Files
24 | 1 | DONE | UI | Hamburger Menu |  |  | Add Hamburger menu to top
25 | 2 |  | UI | slide transistion |  |  | Add slide transitions
26 | 1 |  | error | Better error handling when REST server not available
27 | 1 |  |  | Hearbeat | 24 |  | Settings option to allow for connectivity to REST server to be established
28 | 2 | DONE |  | icons same size |  |  | Should make the tick/cross icons the same size so they do not move the screen when they are changeg
29 | 2 | DONE |  | Should add return from browse playlist to main menu
30 | 2 | DONE |  | Should have an return nav bar on add playlist
31 | 1 | DONE | arch | Repackage pages and pageComponents should be separate
31 | 2 |  |  | styles to css
32 | 2 |  |  | message/alert component |  |  | based on timed messages and success/failure
33 | 2 |  |  | icon config |  |  | move the config styles for icons into config and icon width