## Story
Name | Status | Description
V2 REST pt 1 | IN PRG | The purpose of this is to allow images to be selected from a directory in the images folder rather than only at the top level.
V2 REST pt 2 | READY | The purpose of this is to allow playlists to be stored and selected from a directory rather than just in a flat structure.
Playlist Settings | NO READY | There might be playlist specific settings that are not General Settings
General Settings | READY | There will be general settings such as the number of LEDs on the device
Tidy UI
Tidy Server

## Issues
# | Status | Type | Name | Story | Description
1 |  |  | Track Disable |  | Want to be able to have a temporary omit on a track that stops it from playing. This would mean that I would not have to delete if from the track and re-add (from a nested directory) it to turn it off and on.
2 |  |  | Speed | General Settings | Need to have a play speed on the playlist so that I can vary the movement rate.
3 |  |  | Brightness | General Settings | Would be good to have an overall brightness
4 | DONE |  |  | Tidy UI | Image directory Browser should display the name of the current directory
5 | DONE |  | Remove REST v1/images |  | Remove REST v1/images