## Story
Name | Status | Description
V2 REST pt 1 | IN PRG | The purpose of this is to allow images to be selected from a directory in the images folder rather than only at the top level.
V2 REST pt 2 | READY | The purpose of this is to allow playlists to be stored and selected from a directory rather than just in a flat structure.
Playlist Settings | NO READY | There might be playlist specific settings that are not General Settings
General Settings | READY | There will be general settings such as the number of LEDs on the device
Tidy UI
Tidy Server

## Issues
# | Seq | Priority | Status | Type | Name | Requires | Story | Description
1 |  | 2 | DONE |  | Track Disable Client |  |  | Want to be able to have a temporary omit on a track that stops it from playing. This would mean that I would not have to delete if from the track and re-add (from a nested directory) it to turn it off and on.
2 |  | 1 |  |  | Speed | 35 | General Settings | Need to have a play speed on the playlist so that I can vary the movement rate. Hamburger Menu
3 |  | 1 |  |  | Brightness | 35 | General Settings | Would be good to have an overall brightness Hamburger Menu
4 |  |  | DONE | UI |  |  | Tidy UI | Image directory Browser should display the name of the current directory
5 |  |  | DONE | Arch | Remove REST v1/images |  |  | Remove REST v1/images
6 |  |  | DONE | UI | Tidy image browser buttons |  | Tidy UI | Make buttons on image browser not full width … like the ones on the home page
7 |  |  | DONE | UI | Make browse playlist mode visible |  | Tidy UI
8 |  |  | DONE | UI | Add playlist |  | Tidy UI | make heading h4 and buttons same as on home
9 |  |  | DONE | BUG |  |  |  | Cant save newly created playlist
10 |  |  | DONE | UI | Play Playlist tidy |  | Tidy UI | H4 and button layout on play playlist screen
11 |  |  | DONE | Server | Exception on directory images |  |  | Exception on playing images in directories
12 |  |  | DONE | UI | Better navigation from edit to play |  |  | Better navigation from edit to play
13 |  | 2 | DONE |  |  | 24 |  | Better Top Navigation … title and hamburger. No code change … fixed as consequnce of other changes
44 |  | 1 | DONE |  | Server side handling for config |  | General Settings | Server side handling for config. Split into 53 and 56
15 |  |  | DONE | tech | remove dirname from path |  |  | Remove dirname from browse images path in app.module.ts
16 |  | 2 | DONE |  | diasble tracks in play mode |  |  | In play mode want to be able to disable tracks Duplicate of 1
17 |  | 1 | DONE |  | add return option to nav | 18
18 |  |  | DONE |  | need header component |  |  | Break header into own component so can drive behaviour
19 |  | 1 | DONE |  | select/unselect all in directory bar |  |  | on browse for images need to put the select all and un select all as buttons on the directory bar to save two buttons on the list at the bottom.
20 |  | 1 | DONE |  | images to playlist return nav |  |  | add return from images to playlist on navbar
21 |  | 1 | DONE | BUG | don’t add directory to playlist |  |  | When adding all images it also adds the directory
22 |  | 1 | DONE | BUG |  |  |  | Playlist save not working. This was caused by Bitdefender Safe Files
24 |  | 1 | DONE | UI | Hamburger Menu |  |  | Add Hamburger menu to top
26 |  | 3 |  |  | Better error handling when REST server not available |  | Error Handling | There is a better approach but this is not done everyhwere yet. This still needs to be done for the repo fetches of data It is kind of obvious as there is no data … and there is the settings option to test connectivity
31 |  | 3 |  |  | styles to css
27 |  | 1 | CLOSED |  | Hearbeat | 35 |  | Settings option to allow for connectivity to REST server to be established - non needed as there is now the poll for change
28 |  | 2 | DONE |  | icons same size |  |  | Should make the tick/cross icons the same size so they do not move the screen when they are changeg
29 |  | 2 | DONE |  | Should add return from browse playlist to main menu
30 |  | 2 | DONE |  | Should have an return nav bar on add playlist
31 |  | 1 | DONE | arch | Repackage pages and pageComponents should be separate
32 |  | 3 | CLOSED |  | message/alert component |  |  | based on timed messages and success/failure this has been done
39 |  | 3 |  |  | need a way to kill and restart server from browser |  |  | need a way to kill and restart server from browser
33 |  | 2 | DONE |  | icon config |  |  | move the config styles for icons into config and icon width
35 |  | 1 | DONE |  | Blank settings page |  |  | Settings page placehold for other stuff
36 |  | 1 | DONE |  | REST server check |  |  | Check connectivity to Server on settings page
37 |  | 1 | DONE |  | REST ping service | 37 |  | Add a rest ping service
38 |  | 1 | DONE | Bug | plus on add image is cross
43 |  | 2 |  |  | Prevent playing unsaved data |  |  | encapsulate playlist into a model and protect the data
14 |  | 5 |  |  |  |  | V2 REST pt 2 | Enable playlist folders
41 |  | 2 | DONE |  | Add track disable to server
42 |  | 1 | DONE |  | upgrade Playlist to use Message Component |  |  | Make the playlist save and play errors use the Message component
25 |  | 5 |  | UI | slide transistion |  |  | Add slide transitions
40 |  | 5 |  | bug |  |  |  | pressing hambuger on settings takes you to main
45 |  | 1 | DONE | issue | need to debounce button
46 |  | 1 | DONE | arch | move /app to /
47 |  | 3 |  | arch | handle 404
48 |  | 1 | DONE | bug | ng bulid failure
49 |  | 3 |  | UI | piW fav icon
50 |  | 3 |  | arch | run on port 80
51 | 2 | 3 |  |  | Need to be able to config debounce timeout |  | General Settings
52 |  | 2 | DONE | arch | REST service for get config |  | General Settings
53 |  | 2 | DONE | arch | REST service for set config |  | General Settings
54 | 1 | 2 |  | arch | repository service for get config |  | General Settings
55 |  | 2 |  | arch | repository service for set config |  | General Settings
56 |  | 2 |  | arch | update internals based on post config
57 |  |  |  | UI | modal library inclusion
58 |  | 2 |  | arch | add playlist page should use message page component
59 |  |  |  |  | should add message when navigating away from playlist and playlist needs saving
60 |  |  |  | arch | of |  |  | import { Observable } from 'rxjs/Observable'; import 'rxjs/add/observable/of';
61 |  |  |  |  | remove checks for null playlists
62 |  |  |  | arch | playlist model